## Color
PROJECT: Color
Auto-Bumper |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Joseph Pham
Project start date: | 2024-11-11 |  |  |  |  | October | [20 empty] | November
Scrolling increment: | 5 | time axis 2024-10-11 to 2024-12-05
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-10-11 to 2024-12-05
Bid and Purchasing
Requirements Gathering | Goal | jpham | 100% | 2024-10-14 | 1 | 2024-10-14: 2
Request for Quotation (RFQ) Issuance | Milestone | jpham |  | 2024-10-14 | 1 | bar: 2024-10-14
Purchase Order Creation & Approval | Low Risk | jpham | 100% | 2024-10-15 | 4
Backup Supplier Identification | Med Risk | jpham |  | 2024-10-16 | 1
Delivery Tracking & Pre-Inspection Scheduling | On Track | jpham | 100% | 2024-10-29 | 6
Site Preparation & Utility Setup
Initial Site Survey & Utility Mapping | Goal | jpham | 100% | 2024-10-20 | 4 | 2024-10-20: 2; 2024-10-21: 2; 2024-10-22: 2; 2024-10-23: 2
Electrical Load & Compliance Chech/WiFi Signal Strength and Coverage Assessment | Med Risk |  | 100% | 2024-10-22 | 2
Cement Paving Preparation & Framing/Knight Railing Install Coordination/Air Valve Installation and Calibration | Med Risk |  | 100% | 2024-10-24 | 2
Concrete Pour & Curing (1 Day Wait Time)/Knight Railing Installation | Milestone |  |  | 2024-11-11 | 2 | bar: 2024-11-11 to 2024-11-12
WiFi Configuration/Electrical Wiring/Airline Installation | Milestone |  |  | 2024-11-11 | 1 | bar: 2024-11-11
Final Sign-Off for Utilities & Site Readiness | Milestone |  |  | 2024-11-12 | 1 | bar: 2024-11-12
Multispindle Torque Tool Equipment Installation
Pre-Installation Review & Risk Assessment | Goal | jpham | 100% | 2024-11-11 | 1 | 2024-11-11: 2
Rigging & Hoisting Coordination | Low Risk |  | 100% | 2024-11-13 | 2
Equipment Mounting & Mechanical Anchoring | High Risk |  | 100% | 2024-11-13 | 2
Interface Configuration (e.g., PLC or MES integration) | Med Risk | jpham | 100% | 2024-11-15 | 1
Initial Functional Test & Safety Lockout Validation | Milestone |  |  | 2024-11-16 | 1 | bar: 2024-11-16
Issue Troubleshooting and Debugging | On Track | jpham | 100% | 2024-11-16 | 1
Installation Completion Sign-off | Milestone | jpham |  | 2024-11-16 | 1 | bar: 2024-11-16
Testing & Validation
Testing Kickoff & Scope Alignment | Goal | jpham | 100% | 2024-11-17 | 3 | 2024-11-17: 2; 2024-11-18: 2; 2024-11-19: 2
Dry Run & Alignment Check | Low Risk |  | 100% | 2024-11-17 | 1
Torque Program Validation (per specification) | High Risk | jpham | 100% | 2024-11-17 | 3
Feasibility Testing on Pilot Fasteners | Med Risk | jpham | 100% | 2024-11-17 | 3
Error Simulation & Fault Recovery Check | Med Risk | jpham | 100% | 2024-11-17 | 3
Integration Validation (MES, PLC, Dashboard) | High Risk | jpham | 100% | 2024-11-18 | 3
QA Review & Test Sign-off | Milestone |  |  | 2024-11-19 | 1 | bar: 2024-11-19
Final Operator Walkthrough & Safety Training | Low Risk |  | 100% | 2024-11-20 | 5
Validation Report & Documentation Submission | Med Risk | jpham | 100% | 2024-11-20 | 5
Production Handoff & Go-Live Readiness | Milestone | jpham |  | 2024-11-25 | 1 | bar: 2024-11-25